## Summary
Customer Name | Customer B
Environment | UAT
Upgrade Date | 2018-01-07
Upgrade Start Time | 2:30pm
Installer Version | 18.8.2
Lead | Sam G
PRODUCT | INCLUDED? | SOURCE VERSION | TARGET VERSION
A_SW
B_SW | X | 5.6.1 | 6.4.2
C_SW
D_SW | X | 5.2.2 | 7.8.1
E_SW | X | 4.1.0 | 5.2.10

## Playbook
Process Step | Task | Step | Estimated Start Date | Estimated Start Time | Estimated End Time | Assignee | Status | Actual Start Date | Actual Start Time | Actual End Time | Actual Duration (Minutes) | Errors | Additional Notes
b | 1 | abc | 2017-01-07 | 2:30pm | 2:45pm | Joe | Complete | 2018-01-08 | 2:30pm | 2:45pm
d | 2 | def | 2017-01-07 | 2:45pm | 3:15pm | Joe | Complete | 2018-01-08 |  |  | 15 | Something broke
e | 3 | ghi | 2017-01-07 | 3:15pm | 4:30pm | Nancy | Complete | 2018-01-08 | 11:45am | 12:15pm
b | 4 | jkl | 2017-01-07 | 4:30pm | 4:35pm | Joe | Complete | 2018-01-08 | 12:15pm | 1:27pm
g | 5 | mno | 2017-01-07 | 4:35pm | 5:15pm | Fred | Complete | 2018-01-08 | 13:27 | 2:15pm |  | What happened?
a | 6 | pqr | 2017-01-07 | 5:15pm | 6:20pm | Allison | Complete | 2018-01-08 | 2:15pm | 3:30pm

## Meta
Task States | Template Version
Not Started | 1.0.0
In Progress
Blocked
Complete