## Summary
Customer Name | Customer A
Environment | SIT
Upgrade Date | 2018-03-01
Upgrade Start Time | 11:00AM
Installer Version | 18.0.1
Lead | Joe Schmoe
PRODUCT | INCLUDED? | SOURCE VERSION | TARGET VERSION
A_SW | X | 5.6.1 | 6.1.3
B_SW | X | 5.6.1 | 6.4.2
C_SW
D_SW | X | 5.2.2 | 7.8.1
E_SW

## Playbook
Process Step | Task | Step | Estimated Start Date | Estimated Start Time | Estimated End Time | Assignee | Status | Actual Start Date | Actual Start Time | Actual End Time | Actual Duration (Minutes) | Errors | Additional Notes
a | 1 | abc | 2018-03-01 | 11:00am | 11:15 | Joe | Complete | 2018-03-01 | 11:00am | 11:30am |  | This did not go well | Some note
b | 2 | def | 2018-03-01 | 11:15 | 11:45AM | Joe | Complete | 2018-03-01 |  |  | 15
a | 3 | ghi | 2018-03-01 | 11:45am | 12:15pm | Nancy | Complete | 2018-03-01 | 11:45am | 12:15pm
c | 4 | jkl | 2018-03-01 | 12:15pm | 1:15pm | Joe | Complete | 2018-03-01 | 12:15pm | 1:27pm |  | No clue what happened here.
d | 5 | mno | 2018-03-01 | 13:15 | 2:30pm | Fred | Complete | 2018-03-01 | 13:27 | 2:15pm |  |  | Another note
b | 6 | pqr | 2018-03-01 | 2:30pm | 3:15pm | Allison | Complete | 2018-03-01 |  |  | 70 | Wrong command.
e | 7 | stu | 2018-03-01 | 3:15pm | 11:45pm | Joe | Complete | 2018-03-01 | 3:25pm | 12:01am
f | 8 | vwx | 2018-03-01 | 11:45pm | 0:30 | Joe | Complete | 2018-03-02 | 12:01am | 12:45am
a | 9 | yz | 2018-03-02 | 0:30 | 1:15am | Allison | Complete | 2018-03-02 | 0:45 | 1:47am |  | This one was a mess.
e | 10 | absd | 2018-03-02 | 1:15am | 1:30am | Joe | Complete | 2018-03-02 | 1:47am | 1:55am

## Meta
Task States | Template Version
Not Started | 1.0.0
In Progress
Blocked
Complete