## Summary
Customer Name | Customer A
Environment | UAT
Upgrade Date | 2018-01-05
Upgrade Start Time | 11:00AM
Software | Red SW, Blue Component, Green 3rd Party
Installer Version | 18.0.1
Lead | Joe Schmoe

## Playbook
Process Step | Task | Step | Estimated Start Time | Estimated End Time | Assignee | Status | Actual Start Time | Actual End Time | Notes
a | 1 | abc | 11:00am | 11:15 | Joe | Complete | 11:00am | 11:30am | This did not go well
b | 2 | def | 11:15 | 11:45AM | Joe | Complete | 11:30 | 11:45
a | 3 | ghi | 11:45am | 12:15pm | Nancy | Complete | 11:45am | 12:15pm
c | 4 | jkl | 12:15pm | 1:15pm | Joe | Complete | 12:15pm | 1:27pm | No clue what happened here.
d | 5 | mno | 13:15 | 2:30pm | Fred | Complete | 13:27 | 2:15pm
b | 6 | pqr | 2:30pm | 3:15pm | Allison | Complete | 2:15pm | 3:25pm | Wrong command.
e | 7 | stu | 3:15pm | 11:45pm | Joe | Complete | 3:25pm | 12:01am
f | 8 | vwx | 11:45pm | 0:30 | Joe | Complete | 12:01am | 12:45am
a | 9 | yz | 0:30 | 1:15am | Allison | Complete | 0:45 | 1:47am | This one was a mess.
e | 10 | absd | 1:15am | 1:30am | Joe | Complete | 1:47am | 1:55am

## Task States
Not Started
In Progress
Blocked
Complete