## Summary
Customer Name | Customer A
Environment | PROD
Upgrade Date | 2018-01-06
Upgrade Start Time | 11:00AM
Installer Version | 18.0.1
Lead | Jim Someone
PRODUCT | INCLUDED? | SOURCE VERSION | TARGET VERSION
A_SW | X | 5.6.1 | 6.1.3
B_SW | X | 5.6.1 | 6.4.2
C_SW
D_SW | X | 5.2.2 | 7.8.1
E_SW

## Playbook
Process Step | Task | Step | Estimated Start Time | Estimated End Time | Assignee | Status | Actual Start Time | Actual End Time | Actual Duration (Minutes) | Errors | Additional Notes
a | 1 | abc | 11:00am | 11:15 | Joe | Complete | 11:00am | 11:15am
b | 2 | def | 11:15 | 11:45AM | Joe | Complete |  |  | 12
a | 3 | ghi | 11:45am | 12:15pm | Nancy | Complete | 11:27am | 12:30pm
c | 4 | jkl | 12:15pm | 1:15pm | Joe | Complete | 12:30pm | 1:00pm
d | 5 | mno | 13:15 | 2:30pm | Fred | Complete | 1:00pm | 2:30pm
b | 6 | pqr | 2:30pm | 3:15pm | Allison | Complete |  |  | 15 |  | This was interesting
e | 7 | stu | 3:15pm | 11:45pm | Joe | Complete | 2:45pm | 3:05pm
f | 8 | vwx | 11:45pm | 0:30 | Joe | Complete | 3:05pm | 3:56pm |  | Something broke
a | 9 | yz | 0:30 | 1:15am | Allison | Complete | 3:56pm | 4:30pm
e | 10 | absd | 1:15am | 1:30am | Joe | Complete | 4:30pm | 11:05pm

## Task States
Not Started
In Progress
Blocked
Complete